## WorkPlan
CRWP Workplan for 2015-2020
| FY 2015-16 |  | FY 2016-17 |  | FY 2017-18 |  | FY 2018-19 |  | FY 2019-20 |  | FY 2020-21
Program | ongoing | new | ongoing | new | ongoing | new | ongoing | new | ongoing | new | ongoing | new
Basin Analysis: Studies, GIS, Modeling, Water Quality Monitoring Subprogram
USGS Water Quality Monitors | x |  | x |  | x |  | x |  | x |  | x
BGA Toxic Sampling | x |  | x |  | x |  | x |  | x |  | x
Macro invertebrate sampling | x | [6 empty] | x | x |  | x
Summary of Macro Invertabrate Conditions |  |  |  | x
Septic System Monitoring | x |  | x |  | x |  | x |  | x |  | x
Watershed Reliensency Study | [7 empty] | x
Ground water/snow pack study | [5 empty] | x | x
Integrated Water Resource Study | [11 empty] | x
CE-Qual-W2 Modeling - flow targets | [11 empty] | x
BGA Monitoring Study | [5 empty] | x | x
Water Quality Database | [7 empty] | x | x |  | x
Flow Cam Algal ID support | [7 empty] | x | x |  | x
Education and Research Assistance Subprogram
CRWP Interns | x |  | x |  | x |  | x |  | x |  | x
Research Assistance College and Universities |  | x | x
Point Source Evaluation and Mitigation Subprogram
Comment on water quality permits (NPDES, CAFOs, UST, etc.) | x |  | x |  | x |  | x |  | x |  | x
Pollution Prevention P2 Team | x |  | x |  | x |  | x |  | x |  | x
Outreach to HWY 212/224 industrial customers | [5 empty] | x | x |  | x |  | x
Commercial and industrial spill clean up training | [7 empty] | x | x
Participate in PGE license implemenation | x |  | x |  | x |  | x |  | x |  | x
Participate in PGE BGA Team | x |  | x |  | x |  | x |  | x |  | x
Nonpoint Source/Stormwater Evaluation and Mitigation Subprogram
Agicultural Mitigation
Conintue participation in Clackamas PSP | x |  | x |  | x |  | x |  | x |  | x
Pesticide Reduction | x |  | x |  | x |  | x |  | x |  | x
Pesticide Round Up Events |  |  |  | x | x |  | x |  |  |  |  | x
Ag Incentive program survey |  | x
Agicultural Incentive Program |  | x | x |  | x |  | x |  | x |  | x
Conservation Easements | [11 empty] | x
Septic System Mitigation
Septic System Outreach material | x |  | x |  | x |  | x |  | x |  | x
Septic System Workshops | x |  | x |  | x |  | x |  | x |  | x
Septic System Financial Assistance Program | x |  | x |  | x |  | x |  | x |  | x
Recreation Mitigation
Annual River Clean Up Event | x |  | x |  | x |  | x |  | x |  | x
SRF Grant - Interpretative Signage Project |  | x | x
Clean Boater Program support |  | x | x |  | x
Forestry Mitigation
Particpation in Clackamas Stewardship Partners | x |  | x |  | x |  | x |  | x |  | x
Support Decommissioning of Roads | x |  | x |  | x |  | x |  | x |  | x
Riparian Restoration
GIS to identify riparian area priorities |  | x
Support for Riparian restoration projects | [7 empty] | x | x |  | x
Support for VIP program | [11 empty] | x
Urban Development Mitigation
CRBC Support | x |  | x |  | x |  | x |  | x |  | x
Disaster Preparedness and Response Subprogram
Table Top Exercices | x |  | x |  | x |  | x |  | x |  | x
Clackamas Spill Committee | x |  | x |  | x |  | x |  | x |  | x
Emergency Prepardness & Reponse Training for first responders | [5 empty] | x | x |  |  |  | x
Clackamas Watershed Emergency Response System (GRP webtool) |  |  |  | x | x |  | x |  | x |  | x
Hazardous Material Spill Prevention Program |  |  |  | x | x |  | x |  | x |  | x
Clackamas Homeland Security Task Force | x |  | x |  | x |  | x |  | x |  | x
Clackamas Fuel Task Force |  |  |  |  | x |  | x |  | x |  | x
Clackamas Local Emergency Planning Committee | [5 empty] | x | x |  | x |  | x
Public Outreach and Information Sharing Subprogram
CRWP Website | x |  | x |  | x |  | x |  | x |  | x
CRWP Quarterly Newsletter | x |  | x |  | x |  | x |  | x |  | x
CRWP Annual Watershed Tour | x |  | x |  | x |  | x |  | x |  | x
Public Outreach and Education Program | x |  | x |  | x |  | x |  | x |  | x
Youth Education | x |  | x |  | x |  | x |  | x |  | x
Community Events and Presentations | x |  | x |  | x |  | x |  | x |  | x
Partnership Projects | x |  | x |  | x |  | x |  | x |  | x
Outreach Materials | x |  | x |  | x |  | x |  | x |  | x
Conservation Rebates | x |  | x |  | x |  | x |  | x |  | x
Residential Landscape Audits | [5 empty] | x | x |  | x
multifamily program | [9 empty] | x | x
County Business Sustainability Recognition Program |  | x | x |  | x |  | x |  | x |  | x
Watershed Land Use Tracking and Management Subprogram
Assessment
Tracking
Management
Land Acquisition Subprogram
Indentify critical property
Track federal carbon emmission legislation
PGE Stored Water Fee | x |  | x |  | x |  | x |  | x |  | x

## watershed
Source Water Protection programs
5900 | * Note the programs recommended below are based on the Adopted Drinking Water Protection Plan Implementation Plan.
| FISCAL YEAR: 2015-16 | Proposed for | Proposed for
Annual Projects: |  | FY 2015-16 | FY 2015-16
| Reference to Drinking Water Protection Plan Section/Chapter | Individual projects
| Basin Analysis: Studies, GIS & Water Quality Monitoring Subprogram | BGA raw and finished water toxic sampling | 10000
| Basin Analysis: Studies, GIS & Water Quality Monitoring Subprogram | Annual mainstem macro sampling | 10000
| Education and Research Assistance | PSU/CCC Interns | 6000
| Point Source Evaluation and Mitigation Subprogram | P2 Pollution Prevention Team Clackamas Business Outreach | 1000
| Point Source Evaluation and Mitigation Subprogram | Outreach to industrial Customers | 4000
| Nonpoint Source Evaluation and Mitigation Subprogram - Agricultural | CRBC Operational Support | 10000
| Nonpoint Source Evaluation and Mitigation Subprogram - Agricultural | Pesticide Reduction Outreach | 10000
| Nonpoint Source Evaluation and Mitigation Subprogram - Agricultural | Pesticide Reduction - Agicultural Incentives | 10000
| Nonpoint Source Evaluation and Mitigation Subprogram - Septic Systems | Septic System Program workshops and outreach | 5000
| Nonpoint Source Evaluation and Mitigation Subprogram - Recreation mitigation | Annual River Clean Up Event | 4000
| Nonpoint Source Evaluation and Mitigation Subprogram - Recreation mitigation | Boat Ramp Interpretative Signage - IFA/SRF grant | 27000
| Nonpoint Source Evaluation and Mitigation Subprogram - Recreation mitigation | Clean Boater Program - IFA/SRF Grant | 3000
| Nonpoint Source Evaluation and Mitigation Subprogram - Recreation mitigation | GIS for Riparian Area Analysis | 15000
| Disaster Preparedness and Response Subprogram | Spill Committee, Table top exercise, outreach materials | 2500
| Public Outreach and Information Sharing Subprogram | Watershed Tour | 2500
|  | PGE Stored Water Reservation Fee | 8000
|  | Partnership Projects (i.e. studies, monitoring, events) | 5000
| Annual Projects Subtotal |  | 133000
Continual Projects:
| Basin Analysis: Studies, GIS & water quality monitoring sub program | USGS Contact WQ/Streamflow: | 67000
River Mill
Oregon City
Carter Bridge
Streamflow OR City
|  | WQ Utility (Reliance) | 625
|  | Streamflow/WQ Utility (Qwest) | 625
|  | Replacement probes and sensors | 3000
|  | Replacement cable | 625
|  | Solutions | 3000
|  | Phase in of new WQ Sonds | 15500
| Continual Projects Subtotal |  | 74875
| Budget Subtotal |  | 207875
| Total |  | 207875

## public outreach
Public Outreach and Education Program
5100
draft program budget for FY 2015-16
Project/Vendor/Service Types | Purpose/Source/Type | Costs
Youth Education Assembly shows for K-6th grade | Recycleman/Mad Science/Will Hornyak | 14000
Mini Water Grants | Grants for teachers for water education | 5000
Partnership Projects: Landscape/Irrigation workshops/ Demo Garden/Mobile trailer, etc | CWF, CCWET, College, WES, CCSWCD | 5000
Outreach Supplies/Printing |  | 29500
Brochures, activity books, promotional items, supplies for programs and events, RWCP brochures
Conservation Calendar
Audit kits
public outreach piece
Conservation Rebate Program | HF Toilets, rain sensors, hose bib timers, spray nozzels, washing machines | 12000
| Total | 65500